## Project Planner
Victorian Crash Sight (VCS)
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (hrs)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Intial Meeting | 1 | 1 | 17/08/23 | 17/08/23 | 100% | bar: PERIODS (hrs) 1
Work Breakdown Structure and other documentation | 2 | 2 | 17/08/23 | 17/08/23 | 100% | bar: PERIODS (hrs) 2
Project team meeting | 3 | 2 | 17/08/23 | 17/08/23 | 100% | bar: PERIODS (hrs) 4
Define requirements for User interface | 7 | 2 | 19/08/23 | 20/08/23 | 100% | bar: PERIODS (hrs) 6
Define system requirements | 8 | 3 | 21/08/23 | 21/08/23 | 100% | bar: PERIODS (hrs) 8; PERIODS (hrs) 12; PERIODS (hrs) 14; PERIODS (hrs) 16; PERIODS (hrs) 18
Define and Analyse Use cases | 9 | 3 | 23/08/23 | 23/08/23 | 100% | bar: PERIODS (hrs) 11; PERIODS (hrs) 16; PERIODS (hrs) 20; PERIODS (hrs) 22
Analyse Client requirements | 10 | 2 | 24/08/23 | 25/08/23 | 100% | bar: PERIODS (hrs) 14; PERIODS (hrs) 20; PERIODS (hrs) 22; PERIODS (hrs) 24; PERIODS (hrs) 26
Define system components | 11 | 3 | 25/08/23 | 28/08/23 | 100% | bar: PERIODS (hrs) 16; PERIODS (hrs) 22; PERIODS (hrs) 24; PERIODS (hrs) 26; PERIODS (hrs) 28
Identify classes and methods for the system | 12 | 2 | 28/08/23 | 29/08/23 | 100% | bar: PERIODS (hrs) 19
Analyse crash data | 13 | 2 | 30/08/23 | 2023-01-09 | 100% | bar: PERIODS (hrs) 21
Define data subsystems | 14 | 2 | 2023-01-09 | 2023-01-09 | 100% | bar: PERIODS (hrs) 23
Visualisation development | 15 | 2 | 2023-02-09 | 2023-02-09 | 100% | bar: PERIODS (hrs) 25
Develope test cases | 16 | 2 | 2023-02-09 |  | 10%
Write unit tests | 17 | 3 |  |  | 0%
Conduct user acceptence tests | 18 | 2 |  |  | 0%
Analyse issues found in user acceptance test | 19 | 2 |  |  | 0%
create user manuel | 20 | 3 |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%